## Instructions
Instructions for 5-Year Construction Work Plan Status Update
For each County in the 5-Year Construction Work Plan complete the tabs in this worksheet following the instructions below. ALL projects in the 5-Year Construction Work Plan must be included for each County.
County Resolution # | When a project is added to the plan, the County needs to have a resolution requesting the project to be added from their BOCC meeting. This resolution needs to be approved by the District to start preliminary scoping.
Priority # | The District needs to document adherence to their Priority Policy and document the overall rating here. Retain the priority ranking detail with the County Resolution.
County | Enter the County name here.
District # | Enter the County District number here.
Job # | Enter the Job Number as it appears in the 5 Year Construction Work Plan.
Job Description | Enter a brief description of the Job such as Road Name and miles or Bridge Name.
Road/Bridge | Enter whether the project is a road or bridge.
Stage | These stages are in the order of Oklahoma Department of Transportation flow chart of the states of a project and will stay the same for each project.
Original Plan Year | Year the project originated in the 5 Year Construction Work Plan.
Original Budget | Budget when the project first entered the 5 Year Construction Work Plan.
Plan Year | Enter the plan fiscal year each stage of the project is in the 5 Year Construction Work Plan. If the work is estimated to go through more than one fiscal year, enter both year as for example 2024-2025.
CIRB Budget | Enter the funds estimated to be used for each stage of the project as it appears in the 5 Year Construction Work Plan.
Federal Funds | Enter the funds estimated to be used for each stage of the project as it appears in the 5 Year Construction Work Plan.
Tribal Funds | Enter the funds estimated to be used for each stage of the project as it appears in the 5 Year Construction Work Plan.
Encumbered | Enter the dollar amount encumbered for ODOT for each stage of the project.
Project Status | Project status needs to be updated each month for all projects in the District. Status updates need to state where the project is at such as NEPA, project completed on ?/??/??, or any issues that may happening with the project that would push a project stage further into the plan. Issues may include Environmental issues such as beetles, ROW acquisition issues/condemnation, etc. If a project will need to be pushed back in the plan, this needs to be an agenda item in the meeting. If a project is being completely removed from the plan, it needs to be an agenda item with a resolution from the County requesting the project to be removed and why. If a project is being moved earlier in the Plan, this needs to be an agenda item in the meeting.

## County 1
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | 12345 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition | 2021-2022 | 50000 | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation | 2023-2024 | 50000 | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction | 2025 | 300000 | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 2
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 3
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 4
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 5
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 6
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 7
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 8
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 9
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 10
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 11
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 12
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 13
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0

## County 14
County 5-Year Construction Work Plan Status Update
County Resolution # | Priority # | County | District | Job | Job Description | Road/Bridge | Stage | Original Plan Year | Original Budget | Plan Year | CIRB Budget | Federal Funds | Tribal Funds | Encumbered | Project Status
2023-1234 Approved 3/5/23 | 10 | Blaine | 1 | JP 123456 | American Horse 5 miles | Road | Engineering/Environmental | 2020-2021 | 150000 | 2024-2025 | 300000 |  |  | -310000 | completed 11/16/23
[7 empty] | 30% Plan in Hands | [7 empty] | completed on ?/??/??
[7 empty] | ROW Acquisition |  |  | 2026-2027 | 100000 |  |  | -30000 | ROW issues in condemnation, est. push back work into FY27 on plan
65% Plan in Hands
[7 empty] | Utility Relocation |  |  | 2026-2027 | 50000 |  |  | 0
90% Plan in Hands
[7 empty] | Letting/Construction |  |  | 2028 | 600000 |  |  | 0
[7 empty] | Total |  |  |  | 1050000 | 0 | 0 | -340000
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0
Engineering/Environmental
30% Plan in Hands
ROW Acquisition
65% Plan in Hands
Utility Relocation
90% Plan in Hands
Letting/Construction
[7 empty] | Total |  |  |  | 0 | 0 | 0 | 0